## features
sl no | feature | by | priority | version | implemented
1 | * Upload an existing resume in PDF or DOCX format | vivek | 1 | 0.0.1 | 2024-10-10
2 | * Provide a job description for customization | vivek | 1 | 0.0.1 | 2024-10-10
3 | * Generate a customized resume based on the job description | vivek | 1 | 0.0.1 | 2024-10-10
4 | * Download the customized resume as a PDF | vivek | 1 | 0.0.1 | 2024-10-10
5 | * Responsive design with Bootstrap for a better user experience | vivek | 1 | 0.0.1 | 2024-10-10
6 | tracker to see the number of unique users | rahul | 1
7 | backend--containerization to deploy it in gcp | vivek | 1 | 0.0.2 | 2024-10-11
8 | frontend--makerfile to deploy it in gcp | vivek | 1 | 0.0.2 | 2024-10-11
9 | simple live chat to help out users | rahul | 2
10 | remove personalized content from github | shiv | 1 | 0.0.3
11 | cookie to track and ensure that one person does not use more than 10 times | shiv | 1
12 | limit the # of characters for resume and the job description. | shiv | 1 | 0.0.3 | 2024-10-12
13 | provide user sections to craft their resume | rahul | 2
14 | versioning of the api server | vivek | 1 | 0.0.2 | 2024-10-11
15 | preparation for the company - about the company and its customers | shiv | 1
16 | top 10 questions you may be asekd with answers | shiv | 1
17 | provide alternatives for gpt-4o to gemini | vivek | 2
18 | handle pdf creation in the backend | vivek | 1
19 | version in web app | vivek | 1 | 0.0.3 | 2024-10-12
20
21
22
23

## distribute
channel | suggest | shortcomings
friends, family & well wishers | vivek | more positive
Colleges | vivek | may not pay
X | shiv
Instagram | shiv
Google Adwords | shiv